## Action Plan - BLANK
PROJECT NAME | [7 empty] | PROGRESS LOG
Iteration 3 | [7 empty] | Iteration 3
ACTIVITY | RESPONSIBLE | Due Date | STATUS | START | END | NOTES | Date | ACTIVITY | NOTES
#1: Revise Use Case Description | Mohammad/Dilhan |  | In progress | March 6th |  |  | March 4th | Assigned task to everyone
#2: Revise Sequence Diagram | Sanuda/Tomal |  | In Progress
#3: UCD - Custom settings | Tomal |  | In Progress
#4: UCD - Set up the board | Salman |  | In Progress
#5: Sequence Diagram 1 | Mohammad |  | Not Started
#6: Sequence Diagram 2 | Dilhan |  | Not Started
#7: Logical Architecture Diagram | Salman |  | Not Started
#8: 2nd Minor release | Everyone |  | Not Started