## Action Plan - BLANK
PROJECT NAME | [7 empty] | PROGRESS LOG
Iteration 2 | [7 empty] | Iteration 2
ACTIVITY | RESPONSIBLE | Due Date | STATUS | START | END | NOTES | Date | ACTIVITY | NOTES
#1: Revise Use Case Description | Mohammad, Tomal | Feb 21st | In progress | Feb 8th |  |  | Feb 5th | Assigned task to everyone
#2: Revise Domain Model | Salman | Feb 21st | In Progress | Feb 8th |  |  | Feb 8th | Checked progress and Assigned due dates | Planned to meet once in a week till midterms are over.
#3: USD - Display Settings | Tomal | Feb 21st | In Progress | Feb 8th |  |  | Feb 10th | Review progress
#4: USD - Player Settings | Mohammad | Feb 21st | In Progress | Feb 8th
#5: Sequence Diagram 1 | Tomal | March 1st | Not Started
#6: Sequence Diagram 2 | Mohammad | March 1st | Not Started
#7: Class Diagram | Dilhan, Sanuda, Salman | March 1st | Not Started
#8: Minor release | Dilhan, Sanuda, Salman | March 1st | Not Started