## Action Plan - BLANK
PROJECT NAME | [7 empty] | PROGRESS LOG
Iteration 4 | [7 empty] | Iteration 4
ACTIVITY | RESPONSIBLE | Due Date | STATUS | START | END | NOTES | Date | ACTIVITY | NOTES
#1: Design Accounts for Networking | Mohammad&Tomal | March 27th | Finished | March 23rd | March 27th |  | March 19th | Assigned task to everyone
#2: Use of Patterns | Salman | March 27th | Finished | March 23rd | March 27th |  | March 23rd | Review Progress
#3: Junit Testing | Tomal&Dilhan | March 27th | Finished | March 23rd | March 27th |  | March 27th | Review Progress
#4: Documentation | Salman&Sanuda | March 27th | Finished | March 23rd | March 27th |  | March 31st | Review Progress
#5: Final release | Everyone |  | In complete | March 27th | March 27th |  | April 5th | Review Progress